## Cover Page
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint -1
Sprint Backlog Airline Ticket Management System Project ID: A080 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Initial Selection | 2
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 2 | 2 | 0 | 0 | 0 | 0
Task_2 | UI and Model Creation |  |  | Done | 2 | 2 | 0 | 0 | 0 | 0
Task_3 | Database Connection and Business Logic Implementation |  |  | Done | 2 | 2 | 0 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 2 | 2 | 0 | 0 | 0 | 0
User Story #2 | Admin Login | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 1 | 4 | 0 | 0 | 0
Task_2 | UI and Model |  |  | Done | 5 | 5 | 0 | 0 | 0 | 0
Task_3 | Buisness Logic |  |  | Done | 5 | 5 | 0 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 1 | 4 | 0 | 0 | 0
User Story #3 | Admin Home Page | 2
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 2 | 0 | 2 | 0 | 0 | 0
Task_2 | UI and Model Creation |  |  | Done | 2 | 0 | 2 | 0 | 0 | 0
Task_3 | Display News |  |  | Done | 2 | 0 | 0 | 0 | 1 | 0
Task_4 | Unit Test Execution |  |  | Done | 2 | 0 | 0 | 0 | 1 | 0
User Story #4 | User Details | 2
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 2 | 0 | 2 | 0 | 0 | 0
Task_2 | UI Creation |  |  | Done | 2 | 0 | 2 | 0 | 0 | 0
Task_3 | Database Connection and Business Logic Implementation |  |  | Done | 2 | 0 | 2 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 2 | 0 | 2 | 0 | 0 | 0
User Story #5 | Manage Flights | 1
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 1 | 0 | 1 | 0 | 0 | 0
Task_2 | UI Creation |  |  | Done | 1 | 0 | 1 | 0 | 0 | 0
Task_3 | Correct Redirection |  |  | Done | 1 | 0 | 1 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 1 | 0 | 1 | 0 | 0 | 0
User Story #5a |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 5 | 0 | 0 | 0
Task_2 | UI Creation |  |  | Done | 5 | 0 | 5 | 0 | 0 | 0
Task_3 | Business Login Implmentation |  |  | Done | 5 | 0 | 5 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 5 | 0 | 0 | 0
User Story #5b |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 0 | 0 | 5 | 0
Task_2 | UI Creation |  |  | Done | 5 | 0 | 0 | 0 | 5 | 0
Task_3 | Business Login Implmentation |  |  | Done | 5 | 0 | 0 | 0 | 5 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 0 | 0 | 5 | 0
User Story #6 | Schedule Flight | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 3 | 0 | 0 | 3 | 0 | 0
Task_2 | UI Creation |  |  | Done | 3 | 0 | 0 | 3 | 0 | 0
Task_3 | Buisness Logic |  |  | Done | 3 | 0 | 0 | 3 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 3 | 0 | 0 | 3 | 0 | 0
User Story #6a |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 0 | 0 | 0 | 5 | 0 | 0
Task_2 | UI Creation |  |  | Done | 0 | 0 | 0 | 5 | 0 | 0
Task_3 | Form Validation |  |  | Done | 0 | 0 | 0 | 5 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 0 | 0 | 0 | 5 | 0 | 0
User Story #6b |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 0 | 0 | 5 | 0
Task_2 | Database Connection |  |  | Done | 5 | 0 | 0 | 0 | 5 | 0
Task_3 | Correct Redirection |  |  | Done | 5 | 0 | 0 | 0 | 5 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 0 | 0 | 5 | 0
User Story #8 | User Registration | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 3 | 0 | 1 | 0 | 3 | 0
Task_2 | UI Creation |  |  | Done | 3 | 0 | 1 | 0 | 3 | 0
Task_3 | Correct Redirection |  |  | Done | 3 | 0 | 1 | 0 | 3 | 0
Task_4 | Unit Test Execution |  |  | Done | 3 | 0 | 1 | 0 | 3 | 0
User Story #8a |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 0 | 0 | 3 | 0
Task_2 | UI Creation |  |  | Done | 5 | 0 | 0 | 0 | 3 | 0
Task_3 | Form Validation |  |  | Done | 5 | 0 | 0 | 0 | 3 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 0 | 0 | 3 | 0
User Story #8b |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 0 | 0 | 0 | 5
Task_2 | Database Connection |  |  | Done | 5 | 0 | 0 | 0 | 0 | 5
Task_3 | Correct Redirection |  |  | Done | 5 | 0 | 0 | 0 | 0 | 5
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 0 | 0 | 0 | 5
User Story #9 | User Login | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 0 | 5 | 0 | 0
Task_2 | UI Creation |  |  | Done | 5 | 0 | 0 | 5 | 0 | 0
Task_3 | Form Validation |  |  | Done | 5 | 0 | 0 | 5 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 0 | 5 | 0 | 0
User Story #10 | User Home Page | 2
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 2 | 0 | 0 | 0 | 2 | 0
Task_2 | UI Creation |  |  | Done | 2 | 0 | 0 | 0 | 2 | 0
Task_3 | Correct Redirection |  |  | Done | 2 | 0 | 0 | 0 | 2 | 0
Task_4 | Unit Test Execution |  |  | Done | 2 | 0 | 0 | 0 | 2 | 0
User Story #16 | View Profile | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 0 | 5 | 0 | 5
Task_2 | UI Creation |  |  | Done | 5 | 0 | 0 | 5 | 0 | 5
Task_3 | Database Connection |  |  | Done | 5 | 0 | 0 | 5 | 0 | 5
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 0 | 5 | 0 | 5
User Story #17 | View User Details | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 3 | 0 | 0 | 5 | 0 | 3
Task_2 | Database Connection |  |  | Done | 3 | 0 | 0 | 5 | 0 | 3
Task_3 | UI Creation |  |  | Done | 3 | 0 | 0 | 5 | 0 | 3
Task_4 | Unit Test Execution |  |  | Done | 3 | 0 | 0 | 5 | 0 | 3
TOTAL |  |  |  |  | 232 | 20 | 48 | 92 | 74 | 52

## Sprint -2
Sprint Backlog Airline Ticket Management System Project ID: A080 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #11 | Book Tickets | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 0 | 5 | 0 | 0 | 0
Task_2 | UI Creation |  |  | Done | 5 | 0 | 5 | 0 | 0 | 0
Task_3 | Business Login Implementation and Database Connection |  |  | Done | 5 | 0 | 5 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 0 | 5 | 0 | 0 | 0
User Story #11a |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_2 | UI Creation |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_3 | Redirection |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
User Story #11b |  | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_2 | UI Creation |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_3 | Database Connection |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
User Story #11c |  | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_2 | Business Login Implement |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_3 | Database Connection |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
User Story #11d |  | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_2 | UI Creation |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_3 | Database Connection |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
User Story #14 | Available Seats | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_2 | Business Login Implement |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_3 | Database Connection |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | In Progress | 5 | 0 | 2 | 0 | 0 | 0
User Story #12 | Payment | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_2 | UI Creation |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_3 | Business Login Implementation and Database connection |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | In Progress | 3 | 0 | 1 | 0 | 0 | 0
User Story #13 | Search Option | 3
Task_1 |  |  | RITAM CHAKRABORTY |  | 3 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 0
User Story #15 | View History | 2
Task_1 |  |  | RITAM CHAKRABORTY |  | 2 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0
User Story #18 | Generate Report | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #18a |  | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #18b |  | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #19 | Create Survey | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #19a |  | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #20 | User Feedback | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #21 | Survey Result | 5
Task_1 |  |  | RITAM CHAKRABORTY |  | 5 | 0 | 0 | 0 | 0 | 0
Task_2 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_3 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Task_4 |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
User Story #22 | Forget Password | 5
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 5 | 5 | 0 | 0 | 0 | 0
Task_2 | UI Creation |  |  | Done | 5 | 5 | 0 | 0 | 0 | 0
Task_3 | Validation and Database Connection |  |  | Done | 5 | 5 | 0 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 5 | 5 | 0 | 0 | 0 | 0
User Story #23 | Logout | 3
Task_1 | Unit Test Creation |  | RITAM CHAKRABORTY | Done | 3 | 3 | 0 | 0 | 0 | 0
Task_2 | UI Creation |  |  | Done | 3 | 3 | 0 | 0 | 0 | 0
Task_3 | Business Login Implementation |  |  | Done | 3 | 3 | 0 | 0 | 0 | 0
Task_4 | Unit Test Execution |  |  | Done | 3 | 3 | 0 | 0 | 0 | 0
TOTAL |  |  |  |  | 308 | 32 | 56 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A